## Sheet1
|  |  | April | [9 empty] | Mei
|  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16
|  |  | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27
Persiapan | Pemilihan kasus dan algoritma | Pemilihan Kasus | bar: Week 12 18 to Week 12 22
Penentuan Algoritma | bar: Week 12 18 to Week 12 22
Pelaksanaan | Business Understanding | Menentukan Objektif Bisnis | bar: Week 13 25 to Week 13 29
Menentukan Tujuan Bisnis | bar: Week 13 25 to Week 13 29
| Data Understanding | Mengumpulkan Data | bar: Week 14 9 to Week 14 13
Menelaah Data | bar: Week 14 9 to Week 14 13
Memvalidasi Data | bar: Week 14 9 to Week 14 13
| Data Preparation | Memilah data | bar: Week 15 16 to Week 15 19
Membersihkan Data | bar: Week 15 16 to Week 15 19
Mengkonstruksi Data | bar: Week 15 16 to Week 15 19
Menentukan Label Data | bar: Week 15 16 to Week 15 19
Mengintegrasikan Data | bar: Week 15 16 to Week 15 19
| Modeling | Membangun Skenario Pengujian | bar: Week 15 16 to Week 16 27
Membangun Model | bar: Week 15 16 to Week 16 27
| Model Evaluation | Mengevaluasi Hasil Pemodelan | bar: Week 15 16 to Week 16 27
Melakukan Review Proses Pemodelan | bar: Week 15 16 to Week 16 27
| Deployment | Melakukan Deployment Model | bar: Week 15 16 to Week 16 27
Membuat Laporan Akhir Proyek | bar: Week 15 16 to Week 16 27
Sudah dikerjakan
Sedang dikerjakan
Belum dikerjakan